## Slide 1: INSPIRE MIWP 2020 - 2024
Action 2.2 subgroup kick-off meeting
13 December 2021
Action 2.2 “Roadmap for priority-driven implementation”

## Slide 2: Agenda
Welcome
Round table
Action 2.2 presentation / Discussion
Draft work programme / Discussion
Conclusions / Next meeting

## Slide 3: Subgroup members – short introduction
Ine De Visser NL
Paloma Abas Power ES
Jitka Faugnerová CZ
Martin Tuchyňa SK
Chudy Radoslav SK
Erik Obersteiner AT
Aliki Fatourou EL
Marc Leobet FR
Régis Farret FR
Paweł Soczewski PL
Ouns Kissiyar
Stefan Jensen EEA
Hannes Reuter ESTAT
Joeri Robbrecht ENV

## Slide 4: Short recap on the MIWP2024
3 Areas of work
  1. A digital ecosystem for the environment and sustainability (objective 1)
  2. Towards a common implementation landing zone (objectives 2-4)
  3. GreenData4All (objective 5)
6 Core actions
  1.1 Towards a digital ecosystem for the environment and sustainability
  2.1 Need-driven data prioritisation
  2.2 Roadmap for priority-driven implementation
  2.3 Simplification of INSPIRE implementation
  2.4 Central infrastructure components
  3.1 GreenData4all initiative

## Slide 5: Action 2.2 mandate
Issues
Harmonisation for all data in scope of INSPIRE is considered cumbersome.
The broad data scope has lead to strongly deviating data offerings.
Support for harmonised and non-harmonised data sets without negative impact on compliance indicators (added after 65th MIG-T)
Maximize the reuse of national implementations and avoid parallel implementation (evaluation INSPIRE)
Action
Build on data priorities from Action 2.1 and levels of interoperability to define implementation compliance levels.
Identify the flexibilities of the legal framework. Legal compliance has to be assured.
Propose implementation maturity levels based on the level of interoperability, data priorities and identified legal flexibility.
Pilot the proposed maturity levels on selected data sets.

## Slide 6: Action 2.2 mandate
Links /dependencies
Outcome of Action 2.1 Need-driven data prioritisation
Interplay with Action 2.3 Simplification of INSPIRE implementation
Feed into Action 3.1 GreenData4All
Objective
Rendering a common and comparable implementation of the INSPIRE Directive across Europe more feasible and cost-effective based on common use cases, data priorities and fit-for-purpose interoperability levels.
Support as-is data without negative impact on compliance indicators, maximizing reuse of existing implementations.
Deliverables
Phase 1: Maturity levels proposal, including possible impact on existing implementation.
Phase 2: Develop good practices that implement the maturity levels and pilot these.
Phase 3: Develop additional guidance where needed for application of the maturity levels.

## Slide 7: MIG mini-Workshop (17 June 2021) Harmonised and non-harmonised data sets in INSPIRE
The workshop was guided by a survey to which 22 experts from 21 countries have participated:
  Austria, Belgium (x2), Croatia, Czechia, Denmark, Estonia, France, Germany, Greece, Hungary, Italy, Liechtenstein, Luxembourg, Netherlands, Norway, Poland, Portugal, Slovak Republic, Slovenia, Spain, Sweden.
Main take aways
  The discussion has shown that countries are already using/ preferring different technical solutions. The situation in MS is very different. Support for a mix of proposed technical solutions is preferred.
  An important argument for different metadata records is that in some cases, different data providers are responsible for the harmonised and non-harmonised datasets, which in turn require different metadata records.
  Appreciation of non-harmonized data is strong. Some data cannot be harmonized and is needed for national use cases. INSPIRE harmonized data have limited national/regional/local use.
  Proposal to make the calculation of the indicators more flexible, so it is not needed to choose between the three proposed technical options

## Slide 8: INSPIRE evaluation study – Validation workshop
Validation workshop on 7 September with 72 registered users (10 EC + 7JRC, 36 MS, 19 NGO/private/academics/sectors) of which 61 actually participated.
The results from the validation survey were to a large extent echoed in the workshop and confirmed the findings and recommendations of the study
  91% agreed that there is a need for a more targeted and proportional harmonisation based on use-case driven data priorities in order to reduce costs of implementation.
  81% agreed that the INSPIRE Directive should be implemented as part of the national SDI to increase its relevance and reduce costs.
  72% agreed that there is a need to involve a more diverse representation of stakeholders.
  93% agreed that there is a need to specifically assess the needs of the different user groups in order to prioritise data to be harmonised.
  79% agreed that there are constraints to the use of data shared under INSPIRE, especially for less experienced users.
  72% agreed that there is a need to update Directive 2003/4 on Public access to environmental information so that the spatial data covered by Article 7 is shared in accordance with INSPIRE rules.
Study report - Appendix 6_Workshop report_September 2021

## Slide 9: Additional boundary conditions for our work
  Technical options for publishing non-harmonised datasets can be further elaborated in MIWP Action MIWP 2.3.2 on data-service linking simplification.
  Rich non-harmonized data for national/regional/local use cases should be published under INSPIRE.
  Impact on Member States, Tools and infrastructure should be zero or minimal.
  Need for technical flexibility supporting different approaches
  Look for a legally sound solution (compliant with the current legal framework) supporting a proportionate harmonisation effort in line with the data prioritisation under MIWP Action 2.1.
  Take into consideration the conclusions and recommendations from the evaluation of the INSPIRE Directive. Start gathering evidence on impact and feasibility of future policy options to feed in a possible revision of the legal framework.

## Slide 10: Inception Subgroup Work Programme
Lead
DG ENV
Meeting frequency
Once a month a 1:30 meeting to take stock (last Monday afternoon of the month 14:00-15:30)
Dedicated half day workshops when needed
Subgroup life cycle
Start: December 2021
End: Q4 2022 - Report of subgroup activities with action proposals.

## Slide 11: Inception Work Programme
Phase | Task | Deadline (indicative)
1 | Task 1: Identifying the flexibilities of the legal framework, building on previous simplification efforts. Gather information on national experiences, approaches and data priorities to complement EU level priorities. | 28 February 2022
1 | Task 2: Develop recommendations for data priorities and implementation to come to a feasible and targeted implementation that we can define as common ground. | 28 February 2022
1 | Task 3: Impact assessment of the proposals/recommendations on existing and future implementation. | 28 March 2022 (report for MIG)
2 | Task 4: Where relevant, promote existing or develop new good practices to support a common understanding of the legal obligations and facilitate a common implementation. Pilot the good practices. | 30 Mai 2022 – 26 September 2022
3 | Task 5: Draft guidance (legal, political, technical) on application of maturity levels. | 26 September 2022
1-2-3 | Task 6: Gather recommendations for future improvements to the legal framework | Continuous

## Slide 12: Inception Work Programme – Phase 1
Phase 1: Maturity levels proposal, including possible impact on existing implementation. (28 March 2022)
  Task 1: Identifying the flexibilities of the legal framework, building on previous simplification efforts.
  Task 2: Develop implementation maturity levels.
  Task 3: Impact assessment of the proposal on existing and future implementation.
Draft implementation roadmap proposal to be circulated for feedback and input
  Flexibilities of the legal framework
  Draft proposal for maturity levels – Are different maturity levels needed for all components (metadata, network services, interoperability)?
  Possible good practices to be developed/used to implement the maturity levels
Next meeting to discuss first draft: 31 January 2022.
  Setup Action page on GitHub (ENV)
  ENV to prepare initial draft for input and circulate to subgroup by 17 December 2021
  Subgroup feedback to document by 21 January 2022

## Slide 13: Thank you
© European Union 2020
Unless otherwise noted the reuse of this presentation is authorised under the CC BY 4.0 license. For any use or reproduction of elements that are not owned by the EU, permission may need to be sought directly from the respective right holders.
Notes: Update/add/delete parts of the copy right notice where appropriate.
More information: https://myintracomm.ec.europa.eu/corp/intellectual-property/Documents/2019_Reuse-guidelines%28CC-BY%29.pdf